## Summary
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | [8 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | [8 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date:
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 251 |  |  |  | September | [27 empty] | October
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 1900-09-07 to 1900-11-01
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Cont. Party | Progress | Start | Exp. Start | No. Days |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Pre-Development
| Proforma (volume, 3-5 projection, equipment budget) | On Track |  |  | 100% |  | 12 month Out | 150
| Determine Location | On Track |  |  | 100% |  | 11-12 Month Out | 30
| Determine Debt Gurantee | On Track |  |  | 100% |  | 8-9 Month Out | 30
| Determine Equity Offering | On Track |  |  | 100% |  | 9-10 Month Out | 30
| Determine Governance Structure (Put in Op Agree) | On Track |  |  | 100% |  | 11-12 Month Out | 30
Setup the Accounting System (cash vs. accural)(balance sheet, income statement, cash flow statement)
| Business Plan | On Track |  |  | 100% |  | 10-12 Month Out | 30
L | Letter of Intent | On Track |  |  | 100% |  | 11-12 Month Out | 30
| EIN Number | On Track |  |  | 100% |  | 10-11 Month Out | 15
| Operating Agreement | On Track |  |  | 100% |  | 11-12 Month Out | 30
| Syndication and Raising Equity | Med Risk |  |  | 100% |  | 10-11 Month Out | 30
| Financing | On Track |  |  | 100% |  | 9-10 Month Out | 30
| Architect | Med Risk |  |  | 100% |  | 10-11 Month Out | 30
| Developer, General Contractor | Med Risk |  |  | 100% |  | 9-10 Month Out | 30
Development
| Floor Plan | On Track |  |  | 100% |  | 9-10 Month Out | 90
| Floor Plan to City and Initial DSHS confirmation | On Track |  |  | 100% |  | 8-9 Month Out | 60
| Fixed Equipment/eqipment procurement company | High Risk |  |  | 75% |  | 9-10 Month Out | 90
| MEP Plan to the City | On Track |  |  | 100% |  | 6 Month Out | 30
| Monthly Development Meetings | On Track |  |  | 100% |  | 7-8 Month Out | 150
| Bidding Subcontractors | High Risk |  |  | 100% |  | 5 Month Out | 30
| Permiting and Start of Construction | High Risk |  |  | 100% |  | 4 month Out | 120
| Certificate of Occupancy | On Track |  |  | 50% |  | Obtained 30 to Open | 90
| TDH 50% | On Track |  |  | 50% |  | Half way through Const. | 90
| TDH 100% (CO) | On Track |  |  | 50% |  | End of construction | 30
| Governance (Operating Agreement review and ByLaws) | On Track |  |  | 75% |  | 2 Month Out | 60
| Medical Director | On Track |  |  | 100% |  | 1 Month Out | 30
| Procedure List | On Track |  |  | 100% |  | 4 Month Out (if Possible per Equipment) | 15
| Risk Management | On Track |  |  | 50% |  | 4 Month Out (ADP) | 90
| Licensing- Medicare- 855-B | High Risk |  |  | 94% |  | 6 Month Out (NPI) | 120
| Medicaid Application | On Track |  |  | 0% |  | Immediately p Medicare | 180
| Accreditating Organization | On Track |  |  | 50% |  | 3 Month Out | 90
| TDH Application | On Track |  |  | 90% |  | 3 Month Out | 90
| CLIA Waiver | On Track |  |  | 30% |  | 3 Month Out | 90
| DEA | On Track |  |  | 50% |  | 4-3 Month Out | 90
| Human Resources | On Track |  |  | 50% |  | 4-3 Month Out (ADP) | 90
| Billing Manager (or Outsource) | On Track |  |  | 80% |  | Hire 30-60 Day Out. Review Outsource 4-3 Month Out | 90
| Master Coder | On Track |  |  | 10% |  | Hire 30-60 Day Out. Review Outsource 4-3 Month Out | 90
| Business Office System (MIS) | On Track |  |  | 75% |  | 3-2 Month Out | 90
| EMR | On Track |  |  | 75% |  | 3-2 Month Out | 60
| AR/AP (or Outsource) | On Track |  |  | 10% |  | 4-3 Month Out | 60
| Coding (or Outsource) | On Track |  |  | 10% |  | Hire 30-60 Day Out. Review Outsource 4-3 Month Out | 60
| Payor Contracts (or Outsource) | High Risk |  |  | 50% |  | 6 Month Out | 90
| Ancillary Agreements | On Track |  |  | 0% |  | 1-2 Month Out | 60
| IT systems | Med Risk |  |  | 80% |  | 8-9 Month Out per wiring/data drops | 30
| Website/Marketing | On Track |  |  | 30% |  | 3-2 Month Out | 60
Management
| Materials Management | On Track |  |  | 30% |  | 4 Month Out (Distributor, GPO, Software) | 90
| Movable equipment/Office equipment | On Track |  |  | 30% |  | 4-3 Month Out | 120
| Enterprise Risk Management | On Track |  |  | 20% |  | 4-3 Month Out | 90
| COF | On Track |  |  | 50% |  | 4-3 Month Out | 90
| Accreditating Compliance | On Track |  |  | 50% |  | 4-3 Month Out | 90
| Hiring Administrator/Clinical Director/Leadership | Med Risk |  |  | 100% |  | 4 Month Out | 90
| Hiring Scheduler/Front Desk | On Track |  |  | 20% |  | 2-1 Month Out | 60
| Hiring Staff | Low Risk |  |  | 20% |  | 2-1 Month Out | 60
| Anesthesia | On Track |  |  | 75% |  | 6-4 Month Out | 60
| Pharmacy Consultant | On Track |  |  | 100% |  | 4 Month Out | 60
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one